# CareSys Module Completion and Pending Work Status 27 October 2026

Application web services mobile and website

This report reviews the working local implementation, the remaining module scope and the dependencies required for launch. It is prepared for the product owner to prioritize delivery. The application supports useful agency workflows, but the complete product is not production ready.

# Current position

All 13 selectable agency modules have application workflows. Independent caregivers also have a continuing personal account. The level of completion varies: reporting, deeper care records and financial integrations have substantial remaining scope.

Stripe remains intentionally disabled. Trial, invoice and lock behavior has been tested with simulated provider responses. No real card entry, Stripe payment or money movement has been validated. Existing active commercial agreements are preserved; newly managed agencies follow card setup, module selection, a free period and explicit owner approved payment.

The mobile repository now has a native pairing and billing client. Operational care screens and signed Android or iOS releases are still pending. The website remains separate and was not changed for this review.

# Verified evidence

| Evidence | Latest recorded result |
| --- | --- |
| Backend automated suite | 50 tests and 230 assertions passed |
| Mobile client suite | 5 tests passed |
| New account scenario | 20 checks passed and 16 main evidence images |
| Native build validation | Android and iOS JavaScript exports passed; no signed device binary |

Reviewed revisions: backend 9145b4e; mobile 2497885; website 380a89f. These are source and local evidence checks as of 27 October 2026, not a production certification.

# Module completion overview

Each module below has eight visible review checkpoints in the following pages. Done scores one point, Partial scores half a point, and Pending scores zero. The displayed percentage is rounded checkpoint coverage. It does not measure hours spent, remaining cost, code coverage or production readiness. Advanced features can take much more effort than a basic checkpoint.

These percentages describe the web application and shared backend scope. They do not imply equivalent native mobile screens. The personal account row is a core capability and is not a billable agency seat.

| Module | Done | Partial | Pending | Coverage |
| --- | --- | --- | --- | --- |
| Recruitment and applications | 5 | 1 | 2 | 69% |
| Consented career history | 5 | 1 | 2 | 69% |
| Offers and joining | 5 | 1 | 2 | 69% |
| People administration | 4 | 1 | 3 | 56% |
| Scheduling and visits | 5 | 1 | 2 | 69% |
| Time and attendance | 5 | 1 | 2 | 69% |
| Leave management | 5 | 1 | 2 | 69% |
| Care notes and incidents | 4 | 1 | 3 | 56% |
| Equipment and custody | 4 | 1 | 3 | 56% |
| Expenses | 4 | 1 | 3 | 56% |
| Payroll preparation and exports | 4 | 1 | 3 | 56% |
| Invoices and receipts | 4 | 0 | 4 | 50% |
| Reporting | 3 | 0 | 5 | 38% |
| Independent caregiver account | 6 | 1 | 1 | 81% |

No module is marked production complete. The remaining checkpoint counts include unimplemented functions, partial workflows and external dependencies. The report lists those items explicitly rather than treating a working demo as a finished release.

# Business module detail 1

## Recruitment and applications

Checkpoint coverage 69 percent   Done 5   Partial 1   Pending 2

| Review checkpoint | Status |
| --- | --- |
| Vacancy creation and closing dates | Done |
| Applications and controlled stage changes | Done |
| Purpose based eligible candidate search | Done |
| Private invitation response workflow | Done |
| Pagination and protected profile projection | Done |
| Advanced matching and availability filters | Partial |
| Delivered invitations and verified contact | Pending |
| Restricted identity lookup approved by policy | Pending |

Remaining work: Basic search uses names, regions, role, skills, qualifications and work type. Distance ranking, richer availability matching and actual invitation delivery remain pending. Birth date matching is intentionally disabled pending policy approval.

Evidence: S02 search invite vacancy apply stage; S12 directory and privacy tests

## Consented career history

Checkpoint coverage 69 percent   Done 5   Partial 1   Pending 2

| Review checkpoint | Status |
| --- | --- |
| Attributable career entries | Done |
| Named recipient purpose and bounded grant | Done |
| Candidate selected immutable career versions | Done |
| Expiry withdrawal and access rechecks | Done |
| Disputes and traceable source corrections | Done |
| Disclosure scope across career and extra categories | Partial |
| Authorized external reference responses | Pending |
| Private document disclosure and retention | Pending |

Remaining work: Career version sharing works. Separate reference, qualification and contact disclosure categories, actual reference collection, private binary evidence and retention execution are not complete.

Evidence: S02 requestHistory historyDecision readHistory correctCareer; S12 history tests

# Business module detail 2

## Offers and joining

Checkpoint coverage 69 percent   Done 5   Partial 1   Pending 2

| Review checkpoint | Status |
| --- | --- |
| Revised offer terms and contract digest | Done |
| Separate party agreement with password check | Done |
| Separate individual joining authorization | Done |
| Future dated and idempotent activation | Done |
| Offboarding without moving private history | Done |
| Reviewed onboarding evidence and conditions | Partial |
| Legally validated external signing provider | Pending |
| Advanced overlap and rehire policies | Pending |

Remaining work: Current signing is version specific recorded agreement with password confirmation. It is not a certified digital signature or automated identity check. Manual conditions do not complete a document screening integration.

Evidence: S03 issue contractDecision joiningDecision activate offboard; S12 workflow tests

## People administration

Checkpoint coverage 56 percent   Done 4   Partial 1   Pending 3

| Review checkpoint | Status |
| --- | --- |
| Agency employment and team register | Done |
| Scoped administrative role management | Done |
| Declared and agency accepted qualifications | Done |
| Membership removal and relationship history | Done |
| Full depth personnel record management | Partial |
| Branch and assignment level administration | Pending |
| Secure HR documents and identity evidence | Pending |
| Bulk personnel import and reconciliation | Pending |

Remaining work: Core employee relationships, roles and qualifications are available. A complete HR file, granular branch scopes, evidence uploads and bulk data migration still need implementation and acceptance.

Evidence: S03 offboard; S06 qualification acceptQualification; S07 roles and settings

# Business module detail 3

## Scheduling and visits

Checkpoint coverage 69 percent   Done 5   Partial 1   Pending 2

| Review checkpoint | Status |
| --- | --- |
| Client visit creation and assignment | Done |
| Local timezone and overnight conversion | Done |
| Caregiver overlap prevention | Done |
| Approved leave conflict prevention | Done |
| Current accepted qualification checks | Done |
| Visit outcomes and complete rescheduling | Partial |
| Recurring and multiple caregiver visits | Pending |
| Travel buffers and structured availability | Pending |

Remaining work: Cancellation and no show outcomes are supported. A full reschedule and recurrence workflow, multiworker coverage, travel planning and availability optimization are not delivered.

Evidence: S04 schedule visitDecision instant; S12 overlap and qualification tests

## Time and attendance

Checkpoint coverage 69 percent   Done 5   Partial 1   Pending 2

| Review checkpoint | Status |
| --- | --- |
| Online clock and break state transitions | Done |
| Immutable server timed clock events | Done |
| Actual work duration excluding breaks | Done |
| Duplicate event key protection | Done |
| Version specific review and corrections | Done |
| Finalized period locking and adjustments | Partial |
| Offline capture and conflict safe sync | Pending |
| Native visit capture and location controls | Pending |

Remaining work: Online web capture and correction review work. Payroll exports lock source time, but finalized period reversals need more work. Offline capture, GPS or geofencing and native visit screens are pending.

Evidence: S04 clock elapsed approveTime; S06 correctionDecision; S05 payroll

# Business module detail 4

## Leave management

Checkpoint coverage 69 percent   Done 5   Partial 1   Pending 2

| Review checkpoint | Status |
| --- | --- |
| Own leave request submission | Done |
| Independent approve and reject decisions | Done |
| Overlapping request checks | Done |
| Balance ledger and opening adjustments | Done |
| Cancellation and balance reversal | Done |
| Coverage review notification workflow | Partial |
| Accrual rules and holiday calendars | Pending |
| Jurisdictional paid leave payroll allocation | Pending |

Remaining work: Balance posting, cancellation and adjustments are implemented. Coverage notices remain provider pending. Accrual engines, holiday rules, paid leave calculations and broader race testing remain open.

Evidence: S04 leave leaveDecision; S06 balance; S12 leave tests

## Care notes and incidents

Checkpoint coverage 56 percent   Done 4   Partial 1   Pending 3

| Review checkpoint | Status |
| --- | --- |
| Basic client contacts and instructions | Done |
| Visit related care notes and authorship | Done |
| Incident records with severity | Done |
| Incident acknowledgement | Done |
| Minimum necessary assignment access scope | Partial |
| Versioned care plans and visit tasks | Pending |
| Client consent risk and service agreements | Pending |
| Amendment and escalation ownership workflow | Pending |

Remaining work: This is basic care recording, not a complete clinical record system. Structured plans and tasks, richer client consent and risk records, amendment controls and escalation management remain pending.

Evidence: S04 client note; S06 acknowledge; S07 care and Today data

# Business module detail 5

## Equipment and custody

Checkpoint coverage 56 percent   Done 4   Partial 1   Pending 3

| Review checkpoint | Status |
| --- | --- |
| Tagged equipment register | Done |
| Exclusive current custody with row locking | Done |
| Return condition and custody history | Done |
| Available assigned and maintenance state | Done |
| Full inventory and equipment detail fields | Partial |
| Expected returns and handover acknowledgement | Pending |
| Scheduled maintenance and alerts | Pending |
| Branch stock lost and damaged item workflow | Pending |

Remaining work: Asset assignment, return and a maintenance flag work, including a concurrent assignment test. Serial and category depth, due return control, scheduled maintenance and advanced inventory processes remain open.

Evidence: S04 asset custody; S12 asset concurrency test

## Expenses

Checkpoint coverage 56 percent   Done 4   Partial 1   Pending 3

| Review checkpoint | Status |
| --- | --- |
| Dated category amount and currency input | Done |
| Independent review without self approval | Done |
| Evidence linked reimbursement recording | Done |
| Agency scoped records and audit trail | Done |
| Full draft to payment instruction lifecycle | Partial |
| Mileage and distance reimbursement rules | Pending |
| Private receipt uploads and review | Pending |
| Payroll or payout provider allocation | Pending |

Remaining work: Submission, return, approval and evidenced reimbursement records work. Recording evidence is not a bank transfer. Receipt binaries, mileage and allocation into finalized provider instructions are pending.

Evidence: S04 expense expenseDecision; S12 expense workflow evidence

# Business module detail 6

## Payroll preparation and exports

Checkpoint coverage 56 percent   Done 4   Partial 1   Pending 3

| Review checkpoint | Status |
| --- | --- |
| Approved worked time snapshot | Done |
| Employee provider identity mapping | Done |
| Source locking and duplicate allocation control | Done |
| Checksum and safe CSV download | Done |
| Validation preview and separated batch approval | Partial |
| Paid leave and reimbursement allocation | Pending |
| Provider formats submission and reconciliation | Pending |
| Statutory rules and finalized pay reversals | Pending |

Remaining work: The implemented product is a worked time export, not a payroll payment or statutory tax engine. Provider specific formats, richer approval, paid leave, reimbursement allocation and payroll reconciliation remain pending.

Evidence: S05 employeeMapping payroll csv; S12 payroll and CSV tests

## Invoices and receipts

Checkpoint coverage 50 percent   Done 4   Partial 0   Pending 4

| Review checkpoint | Status |
| --- | --- |
| Agreed rate whole visit invoices | Done |
| Duplicate service allocation protection | Done |
| Partial and full receipt recording | Done |
| Full credits for eligible unpaid invoices | Done |
| Partial quantity and effective dated pricing | Pending |
| Tax partial credit and refund handling | Pending |
| Accounting provider and bank reconciliation | Pending |
| Complete balanced accounting ledger | Pending |

Remaining work: Client billing is separate from CareSys subscription billing. Whole approved visits and evidenced receipts work. Partial visit charging, tax rules, refunds, accounting adapters and a native ledger are not complete.

Evidence: S05 invoice receipt; S06 credit; S12 billing allocation tests

# Business module detail 7

## Reporting

Checkpoint coverage 38 percent   Done 3   Partial 0   Pending 5

| Review checkpoint | Status |
| --- | --- |
| Agency dashboard metric counts | Done |
| Role and module filtered summary visibility | Done |
| Recent actor activity listing | Done |
| Detailed operational and date range reports | Pending |
| Payroll and receivables report catalog | Pending |
| Configurable report exports and filters | Pending |
| Scheduled report delivery | Pending |
| Validated regulatory and management analytics | Pending |

Remaining work: The current Reports page provides scoped counts and recent activity. It is not a comprehensive reporting suite, a report designer or a validated regulatory reporting product.

Evidence: S07 agencyData reports and dashboard; S12 page and tenant checks

## Independent caregiver account

Checkpoint coverage 81 percent   Done 6   Partial 1   Pending 1

| Review checkpoint | Status |
| --- | --- |
| Personal account without an employer | Done |
| Private profile and career maintenance | Done |
| Multiple geography and work preferences | Done |
| Recruiter preview publication and pause | Done |
| Applications offer and joining decisions | Done |
| Qualifications and history permission control | Done |
| Detailed availability and pay preferences | Partial |
| Verified contact and private evidence lifecycle | Pending |

Remaining work: Independent registration, profile control and applying for work are implemented. More structured preferences, production email verification and recovery, restricted identity evidence and document lifecycle remain unfinished.

Evidence: S02 profile visibility career and applications; S06 qualifications; S07 personalData

# Platform and application delivery

The supporting workstreams below are assessed separately from the module percentages. Their gates can prevent launch even when individual local workflows are complete.

## Identity and agency security

Status: Local controls working

Completed: Shield registration and login; agency roles, stale workspace rejection, CSRF and password step up; least privilege database checks.

Pending: Production email verification and recovery, privileged MFA, branch or assignment scopes and an independent authorization review.

Evidence: S07 S09 S13 S14

## Subscriptions trials and payments

Status: Local flow works with live provider disabled

Completed: Versioned module pricing, dependency and worker estimates, immutable descriptive PDFs, configurable free days, exact expiry locks and role specific prompts. Stripe setup and approved payment verification are coded.

Pending: Stripe credentials are deliberately absent. Real test mode card and webhook validation, tax and seller setup, seat metering, proration, cancellation and refund policy remain open.

Evidence: S08 S12

## Browser and mobile web services

Status: Implemented for present workflows

Completed: Separate API host, HTTPS and cookie rejection, one time browser pairing, bounded bearer scope, rate limits and shared business services. Billing status and downloads enforce roles.

Pending: Complete and synchronize OpenAPI contracts, broaden schema and race tests, define compatibility and refresh strategy, then validate production TLS and scale.

Evidence: S09 S12

## Native Android and iOS client

Status: Billing client partial

Completed: Expo client supports pairing, SecureStore, agency access, module choice, estimates, invoice sharing and browser based Stripe approval. Five client tests and both platform JavaScript exports passed.

Pending: Native profile, visits, clocks, leave, care, assets and expense screens; offline and location features; physical device testing; signed packages and store release. Bundles are not installable signed apps.

Evidence: S10 S12

# Supporting services and operations

## Public information website

Status: Independent local site working   Evidence: S11

Completed: Home, About, independent caregivers, modules, subscriptions, tutorials and videos, private contact inbox and moderated feedback. Own process and repository.

Pending: No website change is made in this review. Its public copy does not yet reflect the latest trial and native billing changes. Email or CRM delivery, approved contact details, public HTTPS hosting and launch checks remain open.

## Notifications and provider queue

Status: Records and notices partial   Evidence: S07 S14

Completed: Metadata audit, durable pending provider events and operator queue; immediate login and billing notices for trial expiry.

Pending: Actual email, SMS and push adapters; verified sender and device enrollment; delivery retry and dead letter monitoring. A queued event is not a delivered message.

## Privacy documents and compliance

Status: Consent controls work with wider lifecycle pending   Evidence: S02 S07 S13

Completed: Personal and agency records are separated. Selected career grants support expiry, withdrawal and attributable correction. Agency subscription expiry does not erase personal records.

Pending: Secure uploads and malware scanning, granular extra disclosures, retention and legal hold execution, subject access process, launch jurisdiction and approved signing and screening policies.

## Deployment isolation and recovery

Status: Local separation working   Evidence: S14 S12

Completed: Separate source repositories and local website, portal and API processes. API has separate environment and writable paths. Restricted application database and isolated test schema are verified.

Pending: Docker definitions are prepared but have not been run here. Local processes share a Windows user. Staging and production hosting, managed secrets, monitoring, load targets, encrypted backups and a restore drill remain pending.

## Platform administration and guided forms

Status: Core administration working   Evidence: S07 S08 S13 S14

Completed: Agency verification, manual entitlement agreements, disputes, provider pending queue, free trial policy selector, geography choices and contextual form help.

Pending: Bounded delegated support access, fuller exception and refund handling, deeper availability validation, accessibility acceptance and measured support processes.

# Priority work and release gates

The order below is a proposed delivery sequence. It does not authorize live charging, public deployment or policy restricted features. Owners and dates are not assigned because they have not been agreed.

| Priority | Pending work | Completion evidence needed |
| --- | --- | --- |
| 1 | Production account protection and privacy decisions | Verified sender and recovery, privileged MFA, approved launch jurisdiction, retention and signing decisions. |
| 2 | Stripe test validation and commercial configuration | Real test mode card setup; signed webhook, cancellation, failed payment and retry checks; tax and seller details. Keep live keys disabled until approval. |
| 3 | Staging deployment and recoverability | Built and exercised deployment, trusted TLS, secret management, monitoring, encrypted backup and a measured restore. |
| 4 | Native operational care release | Profile, assigned visits, clocks, leave and notes on actual Android and iOS devices; then signed release packages. |
| 5 | Module depth and external providers | Recurring visits, structured care and reporting; chosen payroll and accounting adapters with reconciliation and correct country rules. |
| 6 | Public release acceptance | Broader race, load, accessibility and authorization review; approved website copy and real support and contact delivery. |

## Broader capabilities not yet delivered

A native statutory payroll engine, balanced accounting ledger, certified digital signing, secure document upload and scanning pipeline, automated reference collection, full clinical care planning and advanced scheduling remain pending or later scope. Existing export, acknowledgement and manual review features must not be presented as those completed products.

Restricted birth date matching, sensitive screening and operational cross agency overlap rules require policy decisions. Their disabled state is intentional. No delivery date or completion cost is supported by the available evidence.

# Evidence limits and source map

The most recent trial test created new owner and member accounts, selected modules, issued a USD 69 proposal, checked the exact expiry boundary, tested existing and fresh logins, denied member billing access, and simulated failed, mismatched and successful payment verification. It reset the agency to awaiting card and revoked its test tokens. Stripe configuration stayed disabled. See Test/README.md and Test/results.json.

A UI issue found during that run was corrected: payment approval is disabled when Stripe is unconfigured. Sixteen main evidence images and the captured invoice are retained in Test. The 50 backend tests do not constitute full acceptance coverage of every module; five client tests are not physical device testing.

Older planning and implementation documents contain superseded statements, including 27 tests, no priced catalog, a proposed Flutter app and unselected payments. This dated review uses current services, the Expo source and the latest test evidence for those areas. The website remains intentionally unchanged, so its older roadmap copy is a pending alignment item.

| ID | Source | Use |
| --- | --- | --- |
| S01 | app/Libraries/SubscriptionQuote.php and SubscriptionPricing.php | Current selectable modules and pricing scope |
| S02 | app/Services/RecruitmentService.php | Profiles recruitment consent history and disputes |
| S03 | app/Services/EmploymentService.php | Offers joining activation and offboarding |
| S04 | app/Services/OperationsService.php | Scheduling time leave care assets and expenses |
| S05 | app/Services/FinanceService.php | Payroll snapshots client invoices receipts and CSV |
| S06 | app/Services/ReviewService.php | Qualifications time corrections balances credits incidents |
| S07 | Workspace.php WorkspaceController.php and caresys views under app | Authorization screens metrics and administration |
| S08 | TrialBillingService AgencyAccessService SubscriptionBillingService StripeGateway and billing controllers | Trial policy provider verification and invoice lifecycle |
| S09 | app/Config/Routes.php ApiController MobileController MobileBillingController MobileAuth and SurfaceGate | Explicit API surface authentication and isolation |
| S10 | caresys-mobile README.md App.js src/client.mjs and client tests | Native client scope and validation limits |
| S11 | caresys-website README.md content/site.json server.mjs and public pages | Independent website pages and local inbox |
| S12 | Test/README.md results.json backend-tests.txt mobile-tests.txt and tests/ | Latest scenario and regression evidence |
| S13 | docs functional specification and implementation-status.md | Proposed wider scope and historic remaining work |
| S14 | deploy/local deploy/container app/Commands/WorkQueue.php and security configuration | Local deployment prepared containers and pending delivery adapters |

Repository references: github.com/cdrika/caresys-backend, github.com/cdrika/caresys-mobile and github.com/cdrika/caresys-website. This report contains no passwords, card details or provider credentials.